## Test Cases
TC ID | Bug ID | Module | Test Case Title | Test Steps | Expected Result | Priority | Status | Actual Result | Remarks
TC-001 | BUG-001 | Frontend | Verify Action Button is disabled when no changes are made | 1. Navigate to a screen containing the Action Button (e.g. Edit/Settings screen). 2. Do not make any changes on the screen. 3. Observe the state of the Action Button. 4. Make a change to any field/value. 5. Observe the state of the Action Button again. | Action Button is disabled (greyed out, not clickable) when no changes are made, and becomes enabled only after a change is made. | Medium | Failed | Action Button remains enabled even when no changes have been made on the screen. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-002 | BUG-002 | Frontend | Verify double-clicking a card does not navigate forward twice | 1. Navigate to a screen containing cards (e.g. Home/List screen). 2. Rapidly double-click on a card. 3. Observe the resulting navigation. | App navigates forward only once. No duplicate screen is pushed onto the navigation stack. | High | Failed | Double-clicking on the card still navigates forward twice; duplicate screen is pushed. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-003 | BUG-003 | Backend | Verify OTP is generated, delivered and verified correctly | 1. Trigger an action requiring OTP (e.g. Signup, Login, Forgot Password). 2. Request the OTP. 3. Check OTP is received (SMS/Email) within expected time. 4. Enter the received OTP. 5. Submit for verification. | OTP is generated and delivered without delay, and verification succeeds with the correct OTP; an incorrect/expired OTP is correctly rejected. | High | Failed | OTP issue is still reproducible as originally reported; fix not yet applied. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-004 | BUG-004 | Frontend | Verify "Preferences" label is changed to "QJR Theme" with larger font | 1. Navigate to the Settings screen. 2. Locate the label previously named "Preferences". 3. Compare its text and font size against neighbouring labels. | Label text reads "QJR Theme" and its font size is visibly larger than the other labels on the screen. | Low | Failed | Label still shows "Preferences" with default font size; text/size not updated to "QJR Theme". | Bug still marked "To Do" in bug report — retest once fix is deployed.
TC-005 | BUG-005 | Frontend | Verify "Don't have an account" text is displayed correctly | 1. Navigate to the Login screen. 2. Locate the text near the Sign Up link. | Text correctly reads "Don't have an account" with correct spelling/grammar. | Low | Passed | Text correctly reads "Don't have an account" with correct spelling/grammar. | Fix verified as per bug report status (Done).
TC-006 | BUG-006 | Frontend | Verify unnecessary gaps between words are removed | 1. Navigate to the affected screen(s). 2. Visually inspect the spacing between words in labels/paragraphs. | No unnecessary/extra gaps appear between words; text spacing is consistent and correct. | Low | Passed | No unnecessary/extra gaps appear between words; text spacing is consistent and correct. | Fix verified as per bug report status (Done).
TC-007 | BUG-007 | Frontend | Verify Save Details button is disabled when payment plan is already active | 1. Log in as a user with an already active payment plan. 2. Navigate to the plan/payment details screen. 3. Observe the Save Details button state. 4. Attempt to click the button. | Save Details button is disabled and cannot be clicked when the payment plan is already active. | Medium | Passed | Save Details button is disabled and cannot be clicked when the payment plan is already active. | Fix verified as per bug report status (Done).
TC-008 | BUG-008 | Backend | Verify days are displayed/updated in sorted order | 1. Navigate to a screen listing days (e.g. Preferences screen). 2. Select multiple days out of chronological order (e.g. Friday, then Monday, then Wednesday). 3. Save/observe the displayed order. | Days are displayed and updated in correct sorted (Mon-Sun) order regardless of selection order. | High | Passed | Days are displayed and updated in correct sorted (Mon-Sun) order regardless of selection order. | Fix verified as per bug report status (Done).
TC-009 | BUG-009 | Frontend | Verify onboarding does not incorrectly reappear after re-signup with a deleted email and app kill | 1. Sign up with an email address, then delete that account/email. 2. Sign up again using the same email address. 3. Force close (kill) the app. 4. Reopen the app. | App opens to the correct screen based on the user's actual current state; onboarding does not incorrectly reappear. | High | Passed | App opens to the correct screen based on the user's actual current state; onboarding does not incorrectly reappear. | Fix verified as per bug report status (Done).
TC-010 | BUG-010 | Frontend | Verify only "Invalid email" error message is displayed for invalid email | 1. Navigate to a form with an email field (Login/Signup). 2. Enter an incorrectly formatted email address. 3. Submit the form. 4. Observe the error message(s) shown. | Only a single "Invalid email" message is displayed; no duplicate or extra error messages appear. | Low | Passed | Only a single "Invalid email" message is displayed; no duplicate or extra error messages appear. | Fix verified as per bug report status (Done).
TC-011 | BUG-011 | Backend | Verify previous quote is not briefly shown before the newly selected quote | 1. Select or change the theme/quote. 2. Immediately observe the quote displayed on screen. | Only the newly selected quote is displayed; the previous quote is not shown even briefly. | Medium | Passed | Only the newly selected quote is displayed; the previous quote is not shown even briefly. | Fix verified as per bug report status (Done).
TC-012 | BUG-012 | Frontend | Verify Terms and Conditions / Privacy Policy show real content, not dummy data | 1. Navigate to Settings > Terms and Conditions. 2. Navigate to Settings > Privacy Policy. 3. Review the displayed content. | Both pages display the actual, correct content; no placeholder/dummy/lorem-ipsum text is shown. | Medium | Passed | Both pages display the actual, correct content; no placeholder/dummy/lorem-ipsum text is shown. | Fix verified as per bug report status (Done).
TC-013 | BUG-013 | Backend | Verify notifications are received as expected | 1. Set a notification preference (day/time) in the app. 2. Wait until the scheduled notification time. 3. Observe device notifications. | Notification is received at the scheduled time with the correct content. | High | Passed | Notification is received at the scheduled time with the correct content. | Fix verified as per bug report status (Done).
TC-014 | BUG-014 | Backend | Verify the app does not automatically log the user out every day | 1. Log in to the app. 2. Keep the app installed and leave the session idle/in background. 3. Wait for more than 24 hours without manually logging out. 4. Reopen the app. | User session remains active; app does not automatically log the user out on a daily basis. | High | Passed | User session remains active; app does not automatically log the user out on a daily basis. | Fix verified as per bug report status (Done).
TC-015 | BUG-015 | Frontend | Verify Admin Panel Description textbox supports multiple lines | 1. Log in to Admin Panel. 2. Open the Description textbox (Theme/Quote). 3. Enter text spanning multiple lines. | Textbox accepts and correctly displays multi-line text input. | Low | Passed | Textbox accepts and correctly displays multi-line text input. | Fix verified as per bug report status (Done).
TC-016 | BUG-016 | Frontend | Verify modal box auto-closes after updating the theme | 1. Log in to Admin Panel. 2. Open the Update Theme modal. 3. Update theme details and click Save. | Modal box closes automatically once the update completes successfully. | Low | Passed | Modal box closes automatically once the update completes successfully. | Fix verified as per bug report status (Done).
TC-017 | BUG-017 | Frontend | Verify only one modal box opens while updating the theme | 1. Log in to Admin Panel. 2. Click the Update Theme action multiple times in quick succession. | Only a single instance of the modal box opens, regardless of repeated clicks. | Medium | Passed | Only a single instance of the modal box opens, regardless of repeated clicks. | Fix verified as per bug report status (Done).
TC-018 | BUG-018 | Frontend | Verify "Sub Theme" label is changed to "Quotes" | 1. Log in to Admin Panel. 2. Navigate to the section previously labelled "Sub Theme". | Label correctly reads "Quotes" instead of "Sub Theme" throughout the section. | Low | Passed | Label correctly reads "Quotes" instead of "Sub Theme" throughout the section. | Fix verified as per bug report status (Done).
TC-019 | BUG-019 | Frontend | Verify updated Delete Theme confirmation text is displayed | 1. Log in to Admin Panel. 2. Trigger the Delete Theme action to open the confirmation dialog. | Confirmation dialog shows the correct, updated delete-theme text. | Low | Passed | Confirmation dialog shows the correct, updated delete-theme text. | Fix verified as per bug report status (Done).
TC-020 | BUG-020 | Frontend | Verify Add Theme route/page is accessible | 1. Log in to Admin Panel. 2. Click on the Add Theme option/button. | Add Theme page loads correctly without a broken route or error. | High | Passed | Add Theme page loads correctly without a broken route or error. | Fix verified as per bug report status (Done).
TC-021 | BUG-021 | Backend | Verify Admin Panel search functionality works correctly | 1. Log in to Admin Panel. 2. Navigate to a list screen (e.g. Users/Themes). 3. Enter a valid search term in the search box. | List filters correctly to show only results matching the search term. | High | Passed | List filters correctly to show only results matching the search term. | Fix verified as per bug report status (Done).
TC-022 | BUG-022 | Frontend | Verify back navigation works correctly from Sub Theme to Theme | 1. Log in to Admin Panel. 2. Navigate from Theme screen into a Sub Theme screen. 3. Click the Back button/icon. | App navigates back to the Theme screen correctly. | Medium | Passed | App navigates back to the Theme screen correctly. | Fix verified as per bug report status (Done).
TC-023 | BUG-023 | Frontend | Verify "User Type" field is removed from Admin Panel | 1. Log in to Admin Panel. 2. Navigate to the user list/details screen. | "User Type" field/column is no longer displayed anywhere in the Admin Panel. | Low | Passed | "User Type" field/column is no longer displayed anywhere in the Admin Panel. | Fix verified as per bug report status (Done).
TC-024 | BUG-024 | Backend | Verify sub theme updates correctly | 1. Log in to Admin Panel. 2. Edit an existing sub-theme's details. 3. Save the changes. 4. Refresh/reopen the sub-theme. | Sub-theme is updated successfully and the changes persist after refresh. | High | Passed | Sub-theme is updated successfully and the changes persist after refresh. | Fix verified as per bug report status (Done).
TC-025 | BUG-025 | Backend | Verify deleting one sub-theme does not remove other sub-themes | 1. Log in to Admin Panel. 2. Add multiple sub-themes under a theme. 3. Delete one specific sub-theme. 4. Observe the sub-theme list without refreshing the page. | Only the deleted sub-theme is removed; all other sub-themes remain visible immediately, without requiring a refresh. | High | Passed | Only the deleted sub-theme is removed; all other sub-themes remain visible immediately, without requiring a refresh. | Fix verified as per bug report status (Done).
TC-026 | BUG-026 | Backend | Verify delete user functionality works correctly | 1. Log in to Admin Panel. 2. Navigate to the user list. 3. Select a user and click Delete. 4. Confirm deletion. | Selected user is successfully deleted and no longer appears in the user list. | High | Passed | Selected user is successfully deleted and no longer appears in the user list. | Fix verified as per bug report status (Done).
TC-027 | BUG-027 | Backend | Verify Admin Panel package/user details reflect updated field set | 1. Log in to Admin Panel. 2. Navigate to user/package details. 3. Verify: User Type field is removed, Expiry Date field is present, IsCard true/false field is present, a View button is present in package details, and Theme Name is displayed. | All listed fields match the updated specification exactly (User Type absent; Expiry Date, IsCard, View button and Theme Name present and functional). | Medium | Passed | All listed fields match the updated specification exactly (User Type absent; Expiry Date, IsCard, View button and Theme Name present and functional). | Fix verified as per bug report status (Done).
TC-028 | BUG-028 | Backend | Verify admin user does not appear in the user list | 1. Log in to Admin Panel as admin@gmail.com. 2. Navigate to the user list. | The admin account itself does not appear in the user list. | Medium | Passed | The admin account itself does not appear in the user list. | Fix verified as per bug report status (Done).
TC-029 | BUG-029 | Backend | Verify Admin Panel only opens for admin@gmail.com | 1. Attempt to access the Admin Panel using a non-admin email account. 2. Attempt to access the Admin Panel using admin@gmail.com. | Access is denied for non-admin accounts and granted only for admin@gmail.com. | High | Passed | Access is denied for non-admin accounts and granted only for admin@gmail.com. | Fix verified as per bug report status (Done).
TC-030 | BUG-030 | Frontend | Verify tooltip is displayed on relevant Admin Panel elements | 1. Log in to Admin Panel. 2. Hover over the relevant icon/element that should show a tooltip. | Tooltip appears with the correct descriptive text. | Low | Passed | Tooltip appears with the correct descriptive text. | Fix verified as per bug report status (Done).
TC-031 | BUG-031 | Frontend | Verify all Admin Panel icons render correctly | 1. Log in to Admin Panel. 2. Navigate through each Admin Panel screen. | All expected icons are visible and render correctly with no missing/broken icons. | Medium | Passed | All expected icons are visible and render correctly with no missing/broken icons. | Fix verified as per bug report status (Done).
TC-032 | BUG-032 | Frontend | Verify invalid email validator is present in Admin Panel | 1. Log in to Admin Panel. 2. Navigate to a form containing an email field. 3. Enter an invalid email format. 4. Submit the form. | Validation error is displayed for the invalid email and the form does not submit. | Medium | Passed | Validation error is displayed for the invalid email and the form does not submit. | Fix verified as per bug report status (Done).
TC-033 | BUG-033 | Frontend | Verify ID column is removed and action options show only on hover | 1. Log in to Admin Panel. 2. View a list table (e.g. Users/Themes). 3. Hover over a row. | ID column is not displayed; action options (edit/delete) appear only when hovering over a row. | Low | Passed | ID column is not displayed; action options (edit/delete) appear only when hovering over a row. | Fix verified as per bug report status (Done).
TC-034 | BUG-034 | Backend | Verify correct session timeframe is displayed after re-login following auto logout | 1. Allow the user session to be logged out automatically. 2. Log back in. 3. Check for session/timeframe information displayed. | User is not logged out unexpectedly; if a logout occurs, the correct session timeframe is displayed after logging back in. | Medium | Passed | User is not logged out unexpectedly; if a logout occurs, the correct session timeframe is displayed after logging back in. | Fix verified as per bug report status (Done).
TC-035 | BUG-035 | Frontend | Verify unauthorized user error message remains visible long enough to read | 1. Trigger an unauthorized access scenario (e.g. invalid session/permission). 2. Observe the red error message and note how long it remains visible. | Error message is clearly visible for an adequate duration and is fully readable, not just a brief flash. | Medium | Passed | Error message is clearly visible for an adequate duration and is fully readable, not just a brief flash. | Fix verified as per bug report status (Done).
TC-036 | BUG-036 | Frontend | Verify correct avatar is displayed in Admin Panel | 1. Log in to Admin Panel. 2. Check the avatar/profile image displayed. | Correct avatar image is displayed as per design. | Low | Passed | Correct avatar image is displayed as per design. | Fix verified as per bug report status (Done).
TC-037 | BUG-037 | Frontend | Verify "Add Quotes" button text, position and spacing are updated | 1. Log in to Admin Panel. 2. Navigate to the Quotes section. 3. Check the button's text, alignment (right side) and surrounding spacing. | Button displays the updated text, is positioned on the right side, and spacing is reduced as specified. | Low | Passed | Button displays the updated text, is positioned on the right side, and spacing is reduced as specified. | Fix verified as per bug report status (Done).
TC-038 | BUG-038 | Frontend | Verify updated success message is shown after creating a quote | 1. Log in to Admin Panel. 2. Create a new quote. 3. Observe the success message shown. | Correct, updated success message text is displayed after successful creation. | Low | Passed | Correct, updated success message text is displayed after successful creation. | Fix verified as per bug report status (Done).
TC-039 | BUG-039 | Frontend | Verify updated delete quote confirmation text is displayed | 1. Log in to Admin Panel. 2. Trigger the Delete Quote action. | Confirmation dialog shows the correct, updated delete-quote text. | Low | Passed | Confirmation dialog shows the correct, updated delete-quote text. | Fix verified as per bug report status (Done).
TC-040 | BUG-040 | Frontend | Verify Description textbox displays 2 to 3 lines | 1. Log in to Admin Panel. 2. Open the Description textbox. 3. Observe the default visible height/line count. | Textbox displays 2 to 3 lines of text by default. | Low | Passed | Textbox displays 2 to 3 lines of text by default. | Fix verified as per bug report status (Done).
TC-041 | BUG-041 | Backend | Verify theme updates correctly | 1. Log in to Admin Panel. 2. Edit an existing theme's details. 3. Save the changes. 4. Reopen/refresh the theme. | Theme updates successfully and the changes persist after refresh. | High | Passed | Theme updates successfully and the changes persist after refresh. | Fix verified as per bug report status (Done).
TC-042 | BUG-042 | Frontend | Verify password validator message appears only once | 1. Navigate to a screen with a password field (e.g. Signup/Change Password). 2. Enter an invalid password. 3. Observe the validator message(s). | Validator message appears only once, not duplicated. | Low | Passed | Validator message appears only once, not duplicated. | Fix verified as per bug report status (Done).
TC-043 | BUG-043 | Frontend | Verify Home route is removed | 1. Check the app's navigation menu/routes. | Home route is no longer present or accessible in the app. | Medium | Passed | Home route is no longer present or accessible in the app. | Fix verified as per bug report status (Done).
TC-044 | BUG-044 | Frontend | Verify updated text labels across Quotes flows | 1. Navigate through the Quotes list, creation and update flows. 2. Check each label: "Quotes"→"Quote", "Add Quote", "Quotes Created Successfully", "Quotes Updated Successfully". | All specified labels display the updated wording exactly as required. | Low | Passed | All specified labels display the updated wording exactly as required. | Fix verified as per bug report status (Done).
TC-045 | BUG-045 | Frontend | Verify Update Quote textbox size is increased | 1. Log in to Admin Panel. 2. Open the Update Quote screen. 3. Check the size of the textbox. | Textbox is visibly larger than the previous size and provides adequate space for editing. | Low | Passed | Textbox is visibly larger than the previous size and provides adequate space for editing. | Fix verified as per bug report status (Done).
TC-046 | BUG-046 | Frontend | Verify text content displays properly across the app | 1. Navigate to the previously affected screen(s). 2. Inspect text rendering (truncation, overlap, corruption). | All text content displays fully and correctly with no truncation, overlap, or corruption. | Medium | Passed | All text content displays fully and correctly with no truncation, overlap, or corruption. | Fix verified as per bug report status (Done).
TC-047 | BUG-047 | Frontend | Verify button shows a loader and app does not crash on double-click | 1. Click the button once and observe whether a loader appears. 2. Click the button rapidly twice in succession. | Loader is shown while the action is in progress; app does not crash and the action is not triggered twice. | High | Passed | Loader is shown while the action is in progress; app does not crash and the action is not triggered twice. | Fix verified as per bug report status (Done).
TC-048 | BUG-048 | Frontend | Verify IsCard/Expiry show "N/A" and Premium shows Yes/No when no card is added | 1. Log in to Admin Panel. 2. View details of a user account that has no card added. | IsCard and Expiry fields display "N/A"; Premium field displays "Yes"/"No" instead of true/false. | Medium | Passed | IsCard and Expiry fields display "N/A"; Premium field displays "Yes"/"No" instead of true/false. | Fix verified as per bug report status (Done).
TC-049 | BUG-049 | Backend | Verify graph is displayed on the Admin Panel dashboard | 1. Log in to Admin Panel. 2. Navigate to the Dashboard. | Graph is displayed on the dashboard with correct, accurate data. | Medium | Passed | Graph is displayed on the dashboard with correct, accurate data. | Fix verified as per bug report status (Done).
TC-050 | BUG-050 | Frontend | Verify app does not crash on double-click after adding card details | 1. Add card details on the payment screen. 2. Double-click the Save/Submit button. | App does not crash; the card details are saved only once. | High | Passed | App does not crash; the card details are saved only once. | Fix verified as per bug report status (Done).
TC-051 | BUG-051 | Frontend | Verify payment screen content does not overlap the status bar | 1. Navigate to the Payment screen. 2. Check the top of the screen near the device status bar. | Payment screen content is correctly positioned below the status bar with no overlap. | Medium | Passed | Payment screen content is correctly positioned below the status bar with no overlap. | Fix verified as per bug report status (Done).
TC-052 | BUG-052 | Backend | Verify preference data appears after expired payment and cancelled auto-renewal | 1. Let a user's payment plan expire and cancel auto-renewal. 2. Navigate to the Preferences screen. | Preference data still correctly appears despite the expired/cancelled plan. | Medium | Passed | Preference data still correctly appears despite the expired/cancelled plan. | Fix verified as per bug report status (Done).
TC-053 | BUG-053 | Frontend | Verify Save Changes button remains disabled until a dropdown value is selected | 1. Navigate to the relevant screen containing a dropdown and Save Changes button. 2. Leave the dropdown unselected. 3. Select a value from the dropdown. | Save Changes button stays disabled while the dropdown is unselected, and becomes enabled after a value is selected. | Low | Passed | Save Changes button stays disabled while the dropdown is unselected, and becomes enabled after a value is selected. | Fix verified as per bug report status (Done).
TC-054 | BUG-054 | Frontend | Verify Add Quote and Create Theme buttons share the same design | 1. Log in to Admin Panel. 2. Compare the Add Quote button and Create Theme button (color, size, shape, font). | Both buttons have a consistent, matching design. | Low | Passed | Both buttons have a consistent, matching design. | Fix verified as per bug report status (Done).
TC-055 | BUG-055 | Frontend | Verify text length is consistent between Home and Favorite screens | 1. Navigate to the Home screen and note the relevant text. 2. Navigate to the Favorite screen and compare the equivalent text. | Text length/content is consistent between both screens as per design intent. | Low | Passed | Text length/content is consistent between both screens as per design intent. | Fix verified as per bug report status (Done).
TC-056 | BUG-056 | Frontend | Verify card details placeholder text color is correct | 1. Navigate to Add Card Details screen. 2. Check the placeholder text color in the input fields. | Placeholder text color matches the updated/correct design specification. | Low | Passed | Placeholder text color matches the updated/correct design specification. | Fix verified as per bug report status (Done).
TC-057 | BUG-057 | Backend | Verify payment information updates after card details are changed | 1. Update the card details on the payment screen. 2. Navigate to the payment information screen. | Payment information correctly reflects the newly updated card details. | High | Passed | Payment information correctly reflects the newly updated card details. | Fix verified as per bug report status (Done).
TC-058 | BUG-058 | Frontend | Verify logo is positioned at the bottom-left corner | 1. Navigate to the relevant screen. 2. Check the position of the logo. | Logo is displayed at the bottom-left corner of the screen. | Low | Passed | Logo is displayed at the bottom-left corner of the screen. | Fix verified as per bug report status (Done).
TC-059 | BUG-059 | Frontend | Verify Delete Account appears inside Change Password screen as a bottom TextButton | 1. Navigate to the Change Password screen. 2. Scroll to the bottom of the screen. | Delete Account option is present inside the Change Password screen, positioned at the bottom, styled as a TextButton. | Low | Passed | Delete Account option is present inside the Change Password screen, positioned at the bottom, styled as a TextButton. | Fix verified as per bug report status (Done).
TC-060 | BUG-060 | Backend | Verify account creation succeeds without Internal Server Error | 1. Fill in the signup form with valid details. 2. Submit the form to create the account. | Account is created successfully with no Internal Server Error. | High | Passed | Account is created successfully with no Internal Server Error. | Fix verified as per bug report status (Done).
TC-061 | BUG-061 | Backend | Verify theme selection works without incorrect "User package not found" error | 1. Log in as a user with a valid active package. 2. Select a theme. 3. Confirm the selection. | Theme is selected successfully with no incorrect "User package not found" error. | High | Passed | Theme is selected successfully with no incorrect "User package not found" error. | Fix verified as per bug report status (Done).
TC-062 | BUG-062 | Backend | Verify notification is received after preference change without requiring re-login | 1. Log in and select a new notification preference. 2. Wait for the scheduled notification without logging out. | Notification is received according to the new preference without needing to logout and login again. | High | Passed | Notification is received according to the new preference without needing to logout and login again. | Fix verified as per bug report status (Done).
TC-063 | BUG-063 | Frontend | Verify updated Preferences text and removal of second sentence | 1. Navigate to the Preferences screen. 2. Check the description text. | Second sentence is removed; text reads "Want a different theme? Email Info@quickjesusreminder for a theme request." | Low | Passed | Second sentence is removed; text reads "Want a different theme? Email Info@quickjesusreminder for a theme request." | Fix verified as per bug report status (Done).
TC-064 | BUG-064 | Frontend | Verify Settings screen option order (Change Password above Logout, Delete Account at bottom) | 1. Navigate to the Settings screen. 2. Check the vertical order of Change Password, Logout and Delete Account options. | Change Password appears above Logout, and Delete Account appears at the bottom of the screen. | Low | Passed | Change Password appears above Logout, and Delete Account appears at the bottom of the screen. | Fix verified as per bug report status (Done).
TC-065 | BUG-065 | Frontend | Verify comma after "issues" is removed on the Settings page | 1. Navigate to the Settings page. 2. Locate the text containing the word "issues". | No comma appears immediately after the word "issues". | Low | Passed | No comma appears immediately after the word "issues". | Fix verified as per bug report status (Done).
TC-066 | BUG-066 | Frontend | Verify Sign In screen text, logo position/size and label updates | 1. Navigate to the Sign In screen. 2. Check the updated screen text, logo at bottom-left, increased size of the top logo, updated "New QJR's" text, and "Email" label (previously "Email ID"). | All specified updates are present and correctly displayed on the Sign In screen. | Low | Passed | All specified updates are present and correctly displayed on the Sign In screen. | Fix verified as per bug report status (Done).
TC-067 | BUG-067 | Frontend | Verify "Your Plan" label is added and "You are a paid subscriber." text is removed | 1. Navigate to the plan/subscription screen. | "Your Plan" label is displayed next to the user's plan; "You are a paid subscriber." text no longer appears. | Low | Passed | "Your Plan" label is displayed next to the user's plan; "You are a paid subscriber." text no longer appears. | Fix verified as per bug report status (Done).
TC-068 | BUG-068 | Frontend | Verify "Your QJR's" heading is added to the page | 1. Navigate to the affected page (Home/QJR list screen). | Page displays "Your QJR's" as its heading. | Low | Passed | Page displays "Your QJR's" as its heading. | Fix verified as per bug report status (Done).
TC-069 | BUG-069 | Frontend | Verify Favorites page heading and text updates | 1. Navigate to the Favorites page. 2. Check heading text, and presence of period, description text, and "Get notified" line. | Heading reads "Favorite QJR's"; the period, description text, and "Get notified" line are all removed. | Low | Passed | Heading reads "Favorite QJR's"; the period, description text, and "Get notified" line are all removed. | Fix verified as per bug report status (Done).
TC-070 | BUG-070 | Backend | Verify only live accounts (no test accounts) appear in Admin Control Panel | 1. Log in to Admin Panel. 2. Navigate to the user list. | Only genuine/live user accounts are listed; random test accounts are not shown. | Medium | Passed | Only genuine/live user accounts are listed; random test accounts are not shown. | Fix verified as per bug report status (Done).
TC-071 | BUG-071 | Frontend | Verify logo does not move unexpectedly when keyboard opens on Sign In screen | 1. Navigate to the Sign In screen. 2. Tap on an input field to open the on-screen keyboard. 3. Observe the logo's position. | Logo remains correctly positioned / behaves as designed without shifting unexpectedly upward. | Low | Passed | Logo remains correctly positioned / behaves as designed without shifting unexpectedly upward. | Fix verified as per bug report status (Done).
TC-072 | BUG-072 | Frontend | Verify time selection is blocked until a day is selected in Preferences | 1. Navigate to the Preferences screen. 2. Attempt to select a time without first selecting a day. | Time selection is disabled/prevented until at least one day is selected. | Medium | Passed | Time selection is disabled/prevented until at least one day is selected. | Fix verified as per bug report status (Done).
TC-073 | BUG-073 | Backend | Verify Pay button is clickable after admin sets isPremium to false | 1. As admin, set a user's isPremium field to false via Admin Panel. 2. Log in as that user and navigate to the Pay screen. 3. Tap the Pay button. | Pay button is clickable and initiates the payment flow correctly. | High | Passed | Pay button is clickable and initiates the payment flow correctly. | Fix verified as per bug report status (Done).
TC-074 | BUG-074 | Backend | Verify Premium status updates automatically post-payment and is non-editable in Admin Panel | 1. Complete a payment as a user. 2. Check the Premium status updates automatically. 3. As admin, attempt to edit the Premium status field in Admin Panel. | Premium status updates automatically after successful payment; the field cannot be manually edited in Admin Panel. | High | Passed | Premium status updates automatically after successful payment; the field cannot be manually edited in Admin Panel. | Fix verified as per bug report status (Done).
TC-075 | BUG-075 | Frontend | Verify onboarding flow completes correctly | 1. Perform a fresh app install. 2. Go through the entire onboarding flow. | Onboarding flow completes successfully with no errors or unexpected behaviour at any step. | Medium | Passed | Onboarding flow completes successfully with no errors or unexpected behaviour at any step. | Fix verified as per bug report status (Done).
TC-076 | BUG-076 | Frontend | Verify email message content is correct | 1. Trigger an action that generates an email (e.g. Signup, Notification, Password Reset). 2. Check the received email content. | Email content (subject and body) is correct and free of errors. | Medium | Passed | Email content (subject and body) is correct and free of errors. | Fix verified as per bug report status (Done).
TC-077 | BUG-077 | Frontend | Verify scrolling works correctly on the payment method screen | 1. Navigate to the Payment Method screen. 2. Attempt to scroll through the content. | Screen scrolls smoothly with no lag, freezing, or blocked content. | Medium | Passed | Screen scrolls smoothly with no lag, freezing, or blocked content. | Fix verified as per bug report status (Done).
TC-078 | BUG-078 | Frontend | Verify notifications display date and time text | 1. Trigger or receive a notification. 2. Check the notification content. | Notification displays the correct date and time text along with its message. | Low | Passed | Notification displays the correct date and time text along with its message. | Fix verified as per bug report status (Done).
TC-079 | BUG-079 | Frontend | Verify updated Home screen text message is displayed | 1. Navigate to the Home screen. 2. Check the displayed text message. | Correct, updated text message is displayed on the Home screen. | Low | Passed | Correct, updated text message is displayed on the Home screen. | Fix verified as per bug report status (Done).
TC-080 | BUG-080 | Frontend | Verify updated Favorites screen text message is displayed | 1. Navigate to the Favorites screen. 2. Check the displayed text message. | Correct, updated text message is displayed on the Favorites screen. | Low | Passed | Correct, updated text message is displayed on the Favorites screen. | Fix verified as per bug report status (Done).
TC-081 | BUG-081 | Backend | Verify Change Password functionality works correctly | 1. Navigate to Change Password screen. 2. Enter the correct old password and a valid new password. 3. Submit the form. 4. Log out and log back in using the new password. | Password changes successfully and the user can log in using the new password. | High | Passed | Password changes successfully and the user can log in using the new password. | Fix verified as per bug report status (Done).
TC-082 | BUG-082 | Frontend | Verify updated Preferences screen text is displayed | 1. Navigate to the Preferences screen. 2. Check the displayed text content. | Correct, updated text is displayed on the Preferences screen. | Low | Passed | Correct, updated text is displayed on the Preferences screen. | Fix verified as per bug report status (Done).
TC-083 | BUG-083 | Backend | Verify group selection option is available in Preferences | 1. Navigate to the Preferences screen. 2. Check for a group selection option. 3. Select a group. | Group selection option is available and functions correctly, saving the selected group. | Medium | Passed | Group selection option is available and functions correctly, saving the selected group. | Fix verified as per bug report status (Done).
TC-084 | BUG-084 | Frontend | Verify shadow is applied to all quotes | 1. Navigate to screens displaying quotes (Home/Favorites). 2. Observe the styling of the quote cards. | All quotes consistently display with the shadow styling applied. | Low | Passed | All quotes consistently display with the shadow styling applied. | Fix verified as per bug report status (Done).
TC-085 | BUG-085 | Frontend | Verify Share option shares the quote in image format | 1. Select a quote. 2. Tap the Share option. 3. Choose a target app to share to. | Quote is shared as an image, correctly rendered with its text. | Medium | Passed | Quote is shared as an image, correctly rendered with its text. | Fix verified as per bug report status (Done).
TC-086 | BUG-086 | Frontend | Verify arrow buttons function correctly | 1. Navigate to a screen with arrow navigation (e.g. quote browsing). 2. Tap the left arrow button. 3. Tap the right arrow button. | Arrow buttons correctly navigate to the previous/next item as expected. | Medium | Passed | Arrow buttons correctly navigate to the previous/next item as expected. | Fix verified as per bug report status (Done).
TC-087 | BUG-087 | Backend | Verify quotes appear correctly after changing the group | 1. Navigate to Preferences and change the selected group. 2. Navigate to the screen displaying quotes. | Quotes update and display correctly according to the newly selected group. | High | Passed | Quotes update and display correctly according to the newly selected group. | Fix verified as per bug report status (Done).
TC-088 | BUG-088 | Frontend | Verify validator prevents adding a theme without entering text | 1. Log in to Admin Panel. 2. Attempt to add a new theme with an empty text field. 3. Submit. | Validation error is displayed and the theme is not added without text being entered. | Medium | Passed | Validation error is displayed and the theme is not added without text being entered. | Fix verified as per bug report status (Done).
TC-089 | BUG-089 | Frontend | Verify bottom sheet closes correctly | 1. Trigger a bottom sheet to open. 2. Attempt to close it via the close button and by tapping outside it. | Bottom sheet closes correctly in both scenarios. | Medium | Passed | Bottom sheet closes correctly in both scenarios. | Fix verified as per bug report status (Done).
TC-090 | BUG-090 | Frontend | Verify validator prevents editing a theme with empty text | 1. Log in to Admin Panel. 2. Edit an existing theme and clear its text field. 3. Submit. | Validation error is displayed and the theme is not updated with empty text. | Medium | Passed | Validation error is displayed and the theme is not updated with empty text. | Fix verified as per bug report status (Done).
TC-091 | BUG-091 | Frontend | Verify validator message appears below the field in the Add Quote section | 1. Navigate to the Add Quote section. 2. Trigger a validation error (e.g. leave field empty and submit). | Validator message appears correctly positioned directly below the relevant field. | Low | Passed | Validator message appears correctly positioned directly below the relevant field. | Fix verified as per bug report status (Done).
TC-092 | BUG-092 | Frontend | Verify correct validator message is displayed | 1. Navigate to a form with validation. 2. Trigger the relevant validation scenario. | Correct, relevant validator message is displayed matching the actual validation error. | Medium | Passed | Correct, relevant validator message is displayed matching the actual validation error. | Fix verified as per bug report status (Done).
TC-093 | BUG-093 | Backend | Verify theme deletion does not unintentionally delete other themes | 1. Log in to Admin Panel. 2. Add multiple themes. 3. Delete a specific theme (not "jvjcj"). 4. Check the remaining theme list. | Only the intended theme is deleted; all other themes remain intact and unaffected. | High | Passed | Only the intended theme is deleted; all other themes remain intact and unaffected. | Fix verified as per bug report status (Done).
TC-094 | BUG-094 | Frontend | Verify copied/pasted text does not persist when navigating to a new theme while editing | 1. Open a theme for editing and paste text into a field. 2. Without saving, navigate to a different/new theme. 3. Check the field content on the new theme. | Previously pasted text does not carry over; fields for the new theme reset/load correctly. | High | Passed | Previously pasted text does not carry over; fields for the new theme reset/load correctly. | Fix verified as per bug report status (Done).
TC-095 | BUG-095 | Frontend | Verify "Don't have an account" text is displayed correctly (duplicate check) | 1. Navigate to the Login screen. 2. Locate the text near the Sign Up link. | Text correctly reads "Don't have an account" with correct spelling/grammar. | Low | Passed | Text correctly reads "Don't have an account" with correct spelling/grammar. | Fix verified as per bug report status (Done).

## Summary
Quick Jesus Reminder - Test Case Summary
Total Bugs Covered | 95
Total Test Cases | 95
Frontend Module Bugs | 68
Backend Module Bugs | 27
High Priority | 25
Medium Priority | 30
Low Priority | 40
Passed | 91
Failed | 4