## Sheet1
ID | Bug Title | Status
BUG-001 | Theme text is not visible on dark background images | Open
BUG-002 | Action Button should be Disabled When No Changes Are Made | Open
BUG-003 | Otp screen (didn't recieved code yet) not working | Done
BUG-004 | Forgot Password displays an error for registered Admin/User email (Email login failed (SMTP 535). Update MAIL_USER / MAIL_PASS on the server and restart pm2.) --- Admin | Done
BUG-005 | OTP issue | Done
BUG-006 | Registration email is sent to client email | Done
BUG-007 | Send an email notification to the admin whenever a new request theme or feedback is received. | Done
BUG-008 | Show the “Last Updated” information only on the Admin Panel; users should not see it. | Done
BUG-009 | Add a “Last Update” column to the main Themes page in the Admin Panel. | Done
BUG-010 | When I change themes the “Your QJR’s” changes and and shows 19 of that themes QJRs. It should show the most recent QJRs. | Done
BUG-011 | When logging in with the Hassanosama account, the Theme and Notification Time settings are displayed incorrectly. | Done
BUG-012 | Duplicate quotes are displayed during new registration | Done
BUG-013 | Auto-renew subscription is not triggered after payment expiry | Done
BUG-014 | Remove the user's count from "Left" when rejoining the same theme | Done
BUG-015 | Incorrect "Device verified successfully" error displayed on Restore Purchase | Done
BUG-016 | Display the Logout button when the user's payment has expired after reopening the app | Done
BUG-017 | Unable to log in – "Connection Error" is displayed | Done
BUG-018 | Premium Status text is truncated in the Users table | Done
BUG-019 | When a user selects a theme, leaves it, and then selects the same theme again, the Users Using and Left counters are updated incorrectly. | Done
BUG-020 | Replace "Annual" with "Yearly" throughout the application | Done
BUG-021 | When a quote is selected but the notification time is not selected, closing the app and reopening it causes the Notification screen to lose the selected quote's image and details. | Done
BUG-022 | When a user's payment expires, the updated status is not reflected on the Admin Panel automatically. The Admin Panel only shows the updated payment status after the user opens the app and logs in. | Done
BUG-023 | On the Login screen, The error message displayed is: "Invalid email, password". The error message should be: "Invalid email or password" | Done
BUG-024 | Email keyboard is not displayed on the Forgot Password screen | Done
BUG-025 | Incorrect text displayed on the Forgot Password screen | Done
BUG-026 | "No access token" error is displayed when refreshing Quotes in Continue Without Account mode | Done
BUG-027 | Subscription payment is not working properly | Done
BUG-028 | On the Theme screen, the text always displays "Users" regardless of the count. When the count is 1, the text should be "User" instead of "Users". | Done
BUG-029 | Remove the Phone Number column from the Users list | Done
BUG-030 | User is redirected to the Theme screen after login instead of the Dashboard | Done
BUG-031 | Timezone issue | Done
BUG-032 | "Requested On" date is not displayed in the Request Theme module | Done
BUG-033 | Remove image validation from the Review Theme Request screen | Done
BUG-034 | Theme Name, Theme Description and Quote should start with a capital letter | Done
BUG-035 | Add "Action" label to all tables across the application | Done
BUG-036 | On the Forgot Password screen, entering an email address that does not belong to an admin displays "Invalid" instead of the expected "User not found" message. | Done
BUG-037 | Created Date is not displayed on the Quotes screen -- Admin pannel | Done
BUG-038 | The image formatshould display: PNG, JPG up to 5 MB. | Done
BUG-039 | Review Theme Request modal opens twice | Done
BUG-040 | Cancel button text is not center-aligned in the Delete Quote confirmation modal | Done
BUG-041 | "Data Not Found" is displayed after refreshing the web | Done
BUG-042 | "Manage all quotes" text wraps to the next line on the Quotes Management screen | Done
BUG-043 | Description character counter turns red at the maximum character limit quotes | Done
BUG-044 | Description character counter turns red at the maximum character limit --- theme | Done
BUG-045 | Modal closes when clicking outside the dialog | Done
BUG-046 | Long theme names should be displayed with an ellipsis (...). | Done
BUG-047 | Valid email format validation is missing | Done
BUG-048 | When a user enters an email address that is not registered, the application displays the error message "Access denied: not authorized", which is incorrect. | Done
BUG-049 | Favicon is missing | Done
BUG-050 | Search is not working on the Dashboard | Done
BUG-051 | Theme Image icon is misaligned on the Create Theme screen | Done
BUG-052 | Cancel and Create Theme buttons are positioned too high on the Create Theme screen | Done
BUG-053 | Display the default image icon when no Theme Image is selected --- listing | Done
BUG-054 | Remove "Admin Panel" text below the logo in the navigation drawer | Done
BUG-055 | Remove Full Name, Email, Phone Number, and Premium Status from the User Details section | Done
BUG-056 | On setting screen change “Preferences” to “QJR Theme”. Also make it larger size than the rest. | Done
BUG-057 | Quote Group screen turns black after navigating back | Done
BUG-058 | Duplicate navigation to the Change Theme screen from the QJR Theme screen | Done
BUG-059 | Two upload icons are displayed in the "Upload Theme Image" section | Done
BUG-060 | Quote Group card height is incorrect, causing text truncation | Done
BUG-061 | "Used By" count displays "2+" instead of the exact count on the QJR Theme card. After reopening the app, the Used By count on the QJR Theme card displays "3+". | Done
BUG-062 | QJR Theme card disappears after purchasing a plan and reopening the app | Done
BUG-063 | Currently selected theme is not highlighted on the Change Theme screen | Done
BUG-064 | Payment Plan change request remains in loading state | Done
BUG-065 | Clicking "Continue without account" results in a token error. | Done
BUG-066 | Payment plan is not displayed. | Done
BUG-067 | When we double-click on the card, it navigates forward twice. | Done
BUG-068 | When attempting to delete a quote that is currently assigned to a user, the deletion fails and an Internal Server Error is displayed. | Done
BUG-069 | Purchased plan is shown as "Free" in the Admin panel | Done
BUG-070 | Created Date is not displayed on the Quotes screen -- Admin pannel | Done
BUG-071 | Created Time is not displayed on the Theme screen -- Admin and App | Done
BUG-072 | The "Popular Themes" title is missing -- Admin and App | Done
BUG-073 | Loader is not displayed while the theme image is uploading on the Request a Theme screen | Done
BUG-074 | Validation is missing for Theme Name and Theme Description fields | Done
BUG-075 | Replace navigation arrow with theme description on the Change Theme and QJR Theme screens | Done
BUG-076 | QJR Theme card disappears after purchasing a plan and reopening the app | Done
BUG-077 | On the Request a Theme screen, the "Upload Theme Image" text should displayed in bold. | Done
BUG-078 | Incorrect upload icon is displayed on the Request a Theme screen | Done
BUG-079 | Theme details are missing on the Change Theme screen | Done
BUG-080 | Selection border is cut off for the first and last theme card | Done
BUG-081 | "By Selecting..." text is not center-aligned on the Payment screen | Done
BUG-082 | On the Change Theme screen, if a user selects a theme and navigates back without tapping "Save Changes", the selected theme is still displayed when reopening the screen. The selection resets only after navigating back and reopening the screen a second time. | Done
BUG-083 | After logging out and registering a new user, the Used By count remains 0 until the page is refreshed. | Done
BUG-084 | Default card images are not displayed | Done
BUG-085 | "Description is required" validation message is displayed too low on the Create Theme screen | Done
BUG-086 | Tooltip remains visible after selecting menu from hamburger and does not disappear until user clicks elsewhere on screen. | Done
BUG-087 | Logout option not hiding on clicking Admin | Done
BUG-088 | Hamburger icon displaying cross icon unnecessarily | Done
BUG-089 | Admin Panel | Done
BUG-090 | Incorrect grammar in delete confirmation message. | Done
BUG-091 | Sub-theme on Dashboard should be displayed within Total Quotes | Done
BUG-092 | Delete icon not clickable in Dashboard theme – should be clickable on both text and icons | Done
BUG-093 | Session Expired issue | Done
BUG-094 | UI Overflow Bug on Feedback Screen When Keyboard is Open | Done
BUG-095 | Closing quotation mark is appearing below in the notification | Done
BUG-096 | Double quotation mark appearing in theme description | Done
BUG-097 | Sometimes, the same time gets selected for both the start time and the end time. | Done
BUG-098 | Infinite loader displayed on payment plan after login | Done
BUG-099 | Text needs to be changed.. Don't have an account | Done
BUG-100 | Remove unnecessary gaps between words | Done
BUG-101 | Save Details button should be disabled when payment plan is already active | Done
BUG-102 | Days are not updating in sorted order | Done
BUG-103 | Onboarding screen appears after re-signup with deleted email and app kill | Done
BUG-104 | Error message should only display Invalid email | Done
BUG-105 | A previous motivational quote is shown, then the one that was clicked appears. | Done
BUG-106 | There is dummy data on the Terms and Conditions, Privacy Policy | Done
BUG-107 | Notifications not appearing | Done
BUG-108 | App logs out user automatically every day | Done
BUG-109 | Admin Panel: Description textbox should support multiple lines | Done
BUG-110 | Admin Panel: Modal box should automatically close after updating the theme | Done
BUG-111 | Admin Panel: Only one modal box should open on updating theme. | Done
BUG-112 | Admin Panel: It should be "Quotes" instead of "Sub Theme". | Done
BUG-113 | Admin Panel: Change this text (delete theme) | Done
BUG-114 | Admin Panel: Add theme route is missing | Done
BUG-115 | Admin Panel: Search functionality is not working | Done
BUG-116 | Admin Panel: Back navigation is not working (Sub Theme → Theme) | Done
BUG-117 | Admin Panel: Remove user Type | Done
BUG-118 | Admin Panel: Sub theme is not updating | Done
BUG-119 | Admin Panel: When one sub-theme is deleted, all sub-themes disappear. They only reappear after refreshing. | Done
BUG-120 | Admin Panel: Delete user is not working | Done
BUG-121 | Admin Panel: Remove user type, add only expiry date, add true or false in isCard field, add view button in package, then add details of package, add theme name | Done
BUG-122 | Admin Panel: Admin should not appear in the user list | Done
BUG-123 | Admin Panel: It should open only with this email... admin@gmail.com | Done
BUG-124 | Admin Panel: Add tooltip | Done
BUG-125 | Admin Panel: Add icons | Done
BUG-126 | Admin Panel: Invalid email validator is missing | Done
BUG-127 | Admin Panel: Remove ID. Actions options should appear on hover | Done
BUG-128 | I just went to the app and it looks like it kicked me out. Once I logged back in it didn’t show any time frame. | Done
BUG-129 | A little red text popped up real quick that said something about unauthorized user. | Done
BUG-130 | Admin Panel: Avatar is wrong | Done
BUG-131 | Change text of button "Add Quotes", place it on the right side, and reduce the spacing. | Done
BUG-132 | Change text "Quotes Created Successfully" | Done
BUG-133 | Change this text... delete Quotes | Done
BUG-134 | Description textbox should be 2 or 3 lines | Done
BUG-135 | Theme is not updating | Done
BUG-136 | Password validator is appearing twice | Done
BUG-137 | Remove home route | Done
BUG-138 | Change text: Quotes to Quote, Add Quote, Quotes Created Successfully, Quotes Updated Successfully | Done
BUG-139 | Increase the size of the textbox for Update Quote | Done
BUG-140 | Text content not displaying properly | Done
BUG-141 | The button doesn't have a loader. The app crashes when clicked twice. | Done
BUG-142 | When no card is added to the user's account, the IsCard and Expiry fields should display "N/A" and the Premium field should display "Yes" or "No" instead of "true" and "false" | Done
BUG-143 | There should be a graph on the dashboard | Done
BUG-144 | App Crashes on Double Click After Adding Card Details | Done
BUG-145 | Payment Screen Overlapping With Status Bar | Done
BUG-146 | Preference Data should Appear after Expired Payment & Auto-Renewal Being Cancelled | Done
BUG-147 | Save changes button remains disabled until dropdown is selected | Done
BUG-148 | Add Quote & Create Theme button should be the same | Done
BUG-149 | Text Length Mismatch in "Home" and "Favorite" Screen | Done
BUG-150 | Change Color of Card Details Placeholder | Done
BUG-151 | Payment Information Not Updating After Card Details Change | Done
BUG-152 | Can we move the logo to the bottom left corner. | Done
BUG-153 | Move Delete Account inside Change Password → Bottom TextButton | Done
BUG-154 | Account creation isn't working... it's showing an internal server error | Done
BUG-155 | Theme is not being selected. It's showing "User package not found". | Done
BUG-156 | My account was logged in. I selected the preference but didn’t receive the notification. Then I logged out and logged in again, selected the preference, and the notification came. | Done
BUG-157 | In Preferences, delete the second sentence ("your chosen theme will") and change it to: "Want a different theme? Email Info@quickjesusreminder for a theme request." | Done
BUG-158 | On setting screen move Change Password above Logout. Move Delete Account to the bottom. | Done
BUG-159 | On setting page, remove the comma after the word "issues". | Done
BUG-160 | Uncapitalize the word "Sign". Add logo to the bottom left corner and a larger logo at the top. Change "New QJR’s" to "Your QJR’s are awaiting you". Change "Email ID" to "Email". | Done
BUG-161 | Add "Your Plan" next to their plan and remove the text "You are a paid subscriber." | Done
BUG-162 | This page has no heading. It should say "Your QJR’s". | Done
BUG-163 | This is the Favorites page. It should say "Favorite QJR’s". Remove the period, remove the text underneath, and delete the "Get notified" line. | Done
BUG-164 | Delete all the random test accounts and only have the live accounts showing on the Admin Control Panel. | Done
BUG-165 | The logo moves upward when the keyboard opens (Sign In). | Done
BUG-166 | In Preferences, validation should prevent selecting a time until a day is selected. | Done
BUG-167 | Pay button is not clickable after setting isPremium to false from Admin Panel | Done
BUG-168 | Premium status should be updated automatically after payment and remain non-editable in Admin Panel | Done
BUG-169 | Onboarding issue | Done
BUG-170 | The email message is incorrect. | Done
BUG-171 | There is a scrolling issue on the payment method screen. | Done
BUG-172 | The notifications will display the date and time text. | Done
BUG-173 | The text message on the home screen will be changed. | Done
BUG-174 | The text message on the favorites screen will be changed. | Done
BUG-175 | The change password function is not working correctly. | Done
BUG-176 | The text on the preferences screen will be changed. | Done
BUG-177 | There will be an option to select groups in preferences. | Done
BUG-178 | A shadow will be added to all quotes. | Done
BUG-179 | Clicking on share will share the quote in an image format. | Done
BUG-180 | Arrow butoons are not working. | Done
BUG-181 | After changing the group, quotes are not appearing. | Done
BUG-182 | Theme is being added without adding text --- there is no validator. | Done
BUG-183 | The bottom sheet is not closing. | Done
BUG-184 | Theme is being edited without adding text --- there is no validator. | Done
BUG-185 | The validator does not appear below the field in the add quote section. | Done
BUG-186 | Wrong Validator. | Done
BUG-187 | All themes were being deleted except for jvjcj.. | Done
BUG-188 | When you copy the text while Editing and go to a new theme, the text is already pasted there. | Done
BUG-189 | change text (Don't have account) | Done